## Original Project Plan
Week | Quarter | Task | Description | Difficulty | Time
Week 1 | Q1 | Set up repo | Clone starter code, create venv | 1 | 1 hr
Week 1 | Q1 | Configure CI | Add Makefile + GitHub Actions | 2 | 2 hrs
Week 2 | Q1 | Manual Azure deployment | Deploy using az webapp up | 3 | 3 hrs
Week 2 | Q1 | Test prediction endpoint | Run scripts locally + Azure | 2 | 1 hr
Week 3 | Q1 | Record demo video | Show CI + Azure + prediction | 2 | 1 hr

## Final Project Plan
Task | Planned Time | Actual Time | Notes
CI pipeline | 2 hrs | 1.5 hrs | Went smoothly
Azure deployment | 3 hrs | 4 hrs | Needed troubleshooting
Prediction testing | 1 hr | 1 hr | As expected

## Quarterly Plan
Quarter | Goals
Q1 | Complete CI pipeline + Azure deployment
Q2 | Add Docker + Kubernetes (optional)
Q3 | Improve testing coverage
Q4 | Explore automation or CD