## Yearly Plan
Quarter | Goals
Q1 | Initial Setup & First Deployment
Q2 | Reliability, Monitoring, Pipeline Improvements
Q3 | Automation, IaC, Containerization
Q4 | Security, Optimization, Final Documentation

## Q1
Quarter 1
Goal | Difficulty | Category
Build CI pipeline | High | Development
Deploy ML app to Azure | Medium | Deployment
Complete documentation | Medium | Documentation
Q1 - Weekly Breakdown
Week | Sprint | Feature | Points (Difficulty) | Status
Week 01 | Sprint 1 | Project Analysis | 3 | Todo
Week 02 | Sprint 1 | Understand deliverables | 2 | Todo
Week 03 | Sprint 1 | Set up Azure sandbox | 2 | Todo
Week 04 | Sprint 1 | Set up Cloud Shell | 2 | Todo
Week 05 | Sprint 2 | Clone repo & run app locally | 2 | Todo
Week 06 | Sprint 2 | Install dependencies | 1 | Todo
Week 07 | Sprint 2 | Create GitHub Actions workflow | 3 | Todo
Week 08 | Sprint 3 | Debug CI pipeline | 3 | Todo
Week 09 | Sprint 3 | Deploy using az webapp up | 3 | Todo
Week 10 | Sprint 3 | Validate App Service URL | 1 | Todo
Week 11 | Sprint 4 | Run prediction script | 2 | Todo
Week 12 | Sprint 4 | Write README + screenshots | 2 | Todo
Week 13 | Sprint 4 | Record demo video | 2 | Todo

## Q2
Quarter 2
Goal | Difficulty | Category
Add monitoring | High | Reliability
Improve CI/CD pipeline | Medium | Development
Add logging & error handling | Medium | Stability
Qaurter 2 weekly Breakdown
Week | Sprint | Feature | Points (Difficulty) | Status
Week 14 | Sprint 5 | Add logging | 2 | Todo
Week 15 | Sprint 5 | Add error handling | 2 | Todo
Week 16 | Sprint 5 | Add environment variables | 1 | Todo
Week 17 | Sprint 6 | Add monitoring (Azure Monitor) | 3 | Todo
Week 18 | Sprint 6 | Add health checks | 2 | Todo
Week 19 | Sprint 6 | Improve CI pipeline speed | 2 | Todo
Week 20 | Sprint 7 | Add retry logic for deployment | 2 | Todo
Week 21 | Sprint 7 | Add pipeline notifications | 1 | Todo
Week 22 | Sprint 7 | Review App Service logs | 2 | Todo
Week 23 | Sprint 8 | Improve README | 1 | Todo
Week 24 | Sprint 8 | Add architecture diagram | 2 | Todo
Week 25 | Sprint 8 | Add future improvements section | 1 | Todo
Week 26 | Sprint 8 | Mid‑year review | 1 | Todo

## Q3
Quarter 3
Goal | Difficulty | Category
Add IaC (Terraform) | High | Automation
Containerize app | High | Deployment
Add autoscaling | Medium | Performance
Q3 Breakdown
Week | Sprint | Feature | Points ( Difficulty) | Status
Week 27 | Sprint 9 | Learn Terraform basics | 3 | Todo
Week 28 | Sprint 9 | Create Terraform resource group | 2 | Todo
Week 29 | Sprint 9 | Create Terraform App Service plan | 3 | Todo
Week 30 | Sprint 10 | Containerize app with Docker | 3 | Todo
Week 31 | Sprint 10 | Create Dockerfile | 2 | Todo
Week 32 | Sprint 10 | Test container locally | 2 | Todo
Week 33 | Sprint 11 | Push container to ACR | 3 | Todo
Week 34 | Sprint 11 | Deploy container to App Service | 3 | Todo
Week 35 | Sprint 11 | Add IaC to CI/CD pipeline | 3 | Todo
Week 36 | Sprint 12 | Add load testing | 2 | Todo
Week 37 | Sprint 12 | Add autoscaling rules | 3 | Todo
Week 38 | Sprint 12 | Review infrastructure | 1 | Todo
Week 39 | Sprint 12 | Q3 retrospective | 1 | Todo

## Q4
Quarter 4
Goals
Add security scanning | High | Security
Optimize pipelines | Medium | Performance
Final documentation | Medium | Documentation
Q4 Breakdown
Week | Sprint | Feature | Points ( Difficulty) | Status
Week 40 | Sprint 13 | Add security scanning | 3 | Todo
Week 41 | Sprint 13 | Add dependency scanning | 2 | Todo
Week 42 | Sprint 13 | Add secret scanning | 2 | Todo
Week 43 | Sprint 14 | Optimize CI pipeline | 2 | Todo
Week 44 | Sprint 14 | Optimize CD pipeline | 2 | Todo
Week 45 | Sprint 14 | Add caching | 1 | Todo
Week 46 | Sprint 15 | Improve documentation | 1 | Todo
Week 47 | Sprint 15 | Add final architecture diagram | 2 | Todo
Week 48 | Sprint 15 | Add final screenshots | 1 | Todo
Week 49 | Sprint 16 | Final testing | 2 | Todo
Week 50 | Sprint 16 | Final review | 1 | Todo
Week 51 | Sprint 16 | Prepare final release | 1 | Todo
Week 52 | Sprint 16 | Year‑end retrospective | 1 | Todo